## project
Project Planner
[6 empty] | Period Highlight: |  |  |  |  | 1 |  |  |  | Plan |  |  | Actual |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
| PLAN | PLAN | ACTUAL | ACTUAL | PERCENT
ACTIVITY | START | DURATION | START | DURATION | COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 61 | 62 | 63 | 64 | 65
Class Diagrams | 1 | 5 | 0 | 0 | 0%
Register | 1 | 1 | 0 | 0 | 0%
Upload user photo | 1 | 1 | 0 | 0 | 0%
Upload background image | 1 | 1 | 0 | 0 | 0%
Filters For Image | 1 | 2 | 0 | 0 | 0%
Shapes For Image | 3 | 3 | 0 | 0 | 0%
Paint Tools For Image | 6 | 2 | 0 | 0 | 0%
Text Caption For Image | 8 | 3 | 0 | 0 | 0%
Textures For Image | 11 | 2 | 0 | 0 | 0%
Filters For Video | 13 | 2 | 0 | 0 | 0%
Shapes For Video | 15 | 3 | 0 | 0 | 0%
Textures For Video | 18 | 2 | 0 | 0 | 0%
Login | 1 | 1 | 0 | 0 | 0%
Reset Password | 1 | 1 | 0 | 0 | 0%
DB Creation for Mobile | 4 | 2 | 0 | 0 | 0%
Find Facebook Friends | 7 | 1 | 0 | 0 | 0%
Find Twitter Friends | 7 | 2 | 0 | 0 | 0%
Find Popular Categories | 10 | 1 | 0 | 0 | 0%
Invite Phone Contacts | 12 | 1 | 0 | 0 | 0%
Invite via Email | 12 | 1 | 0 | 0 | 0%
Invite via SMS | 13 | 1 | 0 | 0 | 0%
Discover | 15 | 2 | 0 | 0 | 0%
Camera integration | 18 | 1 | 0 | 0 | 0%
Record Audio | 18 | 1 | 0 | 0
Access Gallery | 18 | 1 | 0 | 0 | 0%
User Profile | 19 | 1 | 0 | 0 | 0%
Posts | 22 | 2 | 0 | 0
Share your Channel | 25 | 2 | 0 | 0 | 0%
Image and feeds from server | 27 | 1 | 0 | 0 | 0%
Share via App/Facebook /Twitter/Email/Tumblr | 28 | 2 | 0 | 0 | 0%
Keepers |  |  | 0 | 0 | 0%
Edit Profile | 29 | 1 | 0 | 0 | 0%
Change Profile Image | 29 | 1 | 0 | 0 | 0%
Change Background Image | 29 | 1 | 0 | 0 | 0%
Set to private | 29 | 1 | 0 | 0 | 0%
Share settings | 31 | 2 | 0 | 0 | 0%
Notification Settings | 33 | 3 | 0 | 0 | 0%
Support | 36 | 1 | 0 | 0 | 0%
About | 36 | 1 | 0 | 0 | 0%
Logout | 36 | 1 | 0 | 0 | 0%