## App Development Activities
Major Modules | Sub Modules | Activities |  | Web Server Activities | Plan Duration (in Days)
Register | Server | Register |  | Servlet for submitting mobile data to server
Upload user photo
|  | Upload background image |  |  | 3
Facebook
Twitter
Login | Server | Login |  | Servlet for fetching user's login data result from server
| Facebook |  |  |  | 1
Twitter
Reset Password | Send request to server via User's mail ID | Reset Password |  | Servlet to send link to user's email ID to reset password | 1
Interface to Reset Password after clicking the link sent in email ID
Home
| Find Friends |  |  | Send request to contacts whose email Id's are available.
|  | Facebook Friends |  |  | 3
Twitter Friends
Popular Categories
Invite Friends
Phone Contacts
|  | Facebook Friends |  |  | 3
|  | Twitter Friends |  | Adding of selected categories to user's table in DB
| Discover | Discussed in Discover Section
| Share your Channel | email |  | Send Link to added email ID's
|  | Facebook |  |  | 2
Twitter
Discover | What's Interesting ? | Image and feeds from server |  | Servlet to get data of particular category
| Friends Activity | Image and feeds from server
| Categories | Image and feeds from server |  |  | 5
| Search for Hashtags | Image and feeds from server
| Search for Usernames | Image and feeds from server
Main Screen | Text type Post | Share via App/Facebook/Twitter/Email/Tumblr |  |  | 2
| Photo | Camera integration
Filters
Shapes
|  | Paint Tools |  |  | 2
|  | Text Caption | Drag and Drop
Textures
Access Gallery
|  | Share via App/Facebook/Twitter/Email/Tumblr |  | If Shared via App, listing to be set in user's DB | 2
| Audio | Record
Pause
|  | Continue |  |  | 3
Access Playlist
Retake
Filters
Backgrounds
|  | Share via App/Facebook/Twitter/Email/Tumblr |  | If Shared via App, listing to be set in user's DB
| Video | Camera integration
Filters
Shapes
Textures
Access Gallery
|  | Share via App/Facebook/Twitter/Email/Tumblr |  | If Shared via App, listing to be set in user's DB
User Settings | Me | User Profile |  | Retrieve and Set Data to server
|  | Posts |  | Fetch Data from server | 1
Keepers
| Friends | Invite Friends | Phone Contacts | Send request to friends whose email ID's are available in phone contact list | 1
Facebook Friends
Twitter Friends
|  | Find Friends | Facebook Friends
Twitter Friends
|  |  | Popular Categories | Return List of popular Categories (Based on average of users love) | 2
| Account | Edit Profile |  | Mobile data to be sent to server to set in user's DB
Change Profile Image
|  | Change Background Image |  |  | 2
Set to private
| Settings | Share settings | Facebook |  | 1
Twitter
|  | Notification Settings |  | Setting to be set in DB | 1
|  | Support | email support | Servlet to send email on request | 1
|  | About |  |  | 1
Logout
Miscellaneous | Splash Screen |  |  |  | 1
| Graphic Designing for Mobile | 2 Resolutions for iPhone (4 and 5) |  |  | 10
4 Resolutions for Android
| Layout Designing on Mobile |  |  |  | 5
| Side list filter | Only Text Posts |  | Query to return data as requested Type
|  | Only Audio Posts |  |  | 1
Only Video Posts
Only Photo Posts
| HashTag Implementation |  |  | Query to search for Hash Tags | 1
Linking to HashTags
| Chronological Order listing of posts |  |  | Joda Time library integration to set time on posts (1 hour ago etc.) | 1
| Image patch up after applying filters |  |  |  | 2
| Progress bar for showing uploads or posts |  |  |  | 1
| Timer Display |  |  |  | 1
| Orientation Support wherever keypad is needed |  |  |  | 1
| Audio Control for Audio and Video recording |  |  |  | 1
Class Diagram | Mobile (Android and iPhone) + Web Services |  |  |  | 4
Database classification and creation | DB Normalization |  |  |  | 2
|  |  |  | Session Class on server | 1
|  |  |  | Security Class on server | 1
Algorithm | Filters
Textures
| Background |  |  |  | 10
Text
Shapes
80

## Algorithm and Implementation
| Filters | Textures | Shapes | Text
Implementation for Photo as per Mobile support | Sepia | Tv | Crop | Different attractive license free fonts
| B & W | Prism | Heart
| Polarize | Blaze | Rhombus
| Sienna | Press | Square
| HDR | Film | Triangle
| X-Pro | Stars | Plus
| Neon | Strain | Star
| Rust | Scratch | Grid
| Haze | Photocopy | Bars
| Amber |  | Circle
| Aqua |  | Stain
| Trace |  | Design
3D
X-Ray
| Wave Filters | Background
Implementation for Audio as per Mobile support | Echo | Upload Funk
| On Stage | Heist
| Speakers | Inspire
| Radio | Lowrider
| Alvin | Tronic
| Demon | Holiday
Club
Lounge
News
Epic
| Filters | Textures | Shapes
Implementation for Video as per Mobile support | Sepia | 8mm
| B & W | Grain | Heart
| Polarize | Stars | Rhombus
| Sienna | Film | Square
| HDR | Blaze | Triangle
| X-Pro | Trip | Plus
| Neon | Rain | Star
| Rust | TV | Grid
| Haze | REC | Bars
| Amber |  | Circle
| Aqua |  | Stain
| Trace |  | Design
3D
X-Ray