## Project Timeline
YOUR PROJECT
TIMELINE
PROJECT DETAILS
DATE | MILESTONE | POSITION | BASELINE
2014-02-20 | Project Start | 25 | 1
2014-02-21 | Class Diagram |  | 1
2014-03-01 | Register | 10 | 1
2014-03-03 | Login | -10 | 1
2014-03-03 | Reset Password | 15 | 1
2014-03-04 | Database classification and creation | -15 | 1
2014-03-07 | Home | 15 | 1
2014-03-11 | Discover | -15 | 1
2014-03-13 | Main Screen | 15 | 1
2014-03-15 | User Settings | -20 | 1
2014-03-17 | Miscellaneous | 20 | 1
2014-03-21 | Algorithm | -15 | 1
2014-04-01 | Project End | 15 | 1
Project Timeline Tips:
The role of the Position values in the Project Details table is to prevent the Milestone labels from overlapping each other on the timeline. Use positive numbers to position labels above the timeline and negative numbers to position them below.
To add additional Milestones, either insert new rows within the table or start typing below the last table entry and the table will automatically expand to accommodate your newly added data.